CHANGE ORDER

No.:  	7

PROJECT: DESIGN/BUILD SERVICES FOR THE CITY OF DANIA BEACH

2.0 MGD NANOFILTRATION WATER TREATMENT PLANT

DATE OF ISSUANCE  	November 28, 2011		EFFECTIVE DATE

OWNER   City of Dania Beach, Florida

OWNER’s Contract No.   Bid No. 09-005		CDM Project No.   74061

CONTRACTOR  CDM Constructors Inc		ENGINEER

You are directed to make the following changes in the Contract Documents:

Description:                        Attachment “A” - Scope of Change Order

Reason for change order: Attachment “A” - Scope of Change Order

Attachments:                      Attachment “A” - Scope of Change Order

| CHANGE IN CONTRACT PRICE Original Contract Price $ 8,820,923.00 | CHANGE IN CONTRACT TIME Original Contract Times Substantial Completion: Ready for final payment: 630 (August 8, 2011) Days or dates |
| --- | --- |
| Net changes from previous Change Orders No. _1___ to No.__6___ $ 335,835.00 | Net change from previous Change Orders No. 1 to No. 6 143 Days |
| Contract Price prior to this Change Order $ 9,176,758.00 | Contract Time prior to this Change Order Substantial Completion: Ready for final payment: 773 (December 29, 2011) Days or dates |
| Net Increase (decrease) in this Change Order $ 0.00 | Net Increase in this Change Order 30 days |
| Contract Price with all approved Change Orders $ 9,176,758.00 | Contract Time with all approved Change Orders Substantial Completion: Ready for final payment: 803 (January 28, 2012) Days or dates |

RECOMMENDED BY:			APPROVED BY:	ACCEPTED BY:

Engineer (Authorized Signature)			Owner (Authorized Signature)	Contractor (Authorized Signature)

Date:  					Date:  			Date:

CHANGE ORDER

TO:	City of Dania Beach, Florida

PROJECT: DESIGN/BUILD SERVICES FOR THE CITY OF DANIA BEACH

2.0 MGD NANOFILTRATION WATER TREATMENT PLANT

CONTRACTOR:	CDM Constructors Inc.

DATE:	 November 28, 2011

This Change Order will authorize the following change to the Agreement:

The Work as set forth in the Agreement is amended to include the items set forth in Attachments “A” and by this reference made a part of this document.

Net Change to Contract from this Change Order			$0.00		       30 days

This Change Order constitutes full, final, and complete authorization for compensation to the Contractor for all costs, expenses, overhead, and profit, and any damages of every kind that the Contractor may incur in connection with the above referenced change(s) in the Work, and any other effect on any of the Work under this Agreement. The Contractor acknowledges and agrees that (a) the Lump Sum of $8,820,923.00 under the Agreement will be unchanged by this Change Order, and (b) the schedule of performance of Work will be unchanged by this Change Order. Contractor expressly waives any claims for any additional compensation, damages or time extensions in connection with the above referenced change(s). Except as modified by the document, all terms of the Agreement shall remain in full force and effect and shall cover the performance of, and payment for, any work authorized under this document. Any defined terms not defined in this Change Order shall have the meanings set forth in the Agreement.

By signing below the parties indicate acceptance of this Change Order as set forth in it.

CONTRACTOR	CITY OF DANIA BEACH,

CDM Constructors Inc.	a Florida municipal corporation

a Florida corporation

By:			By:

Robert Baldwin, City Manager

Name:			Authorized by action of City Commission

Title:			of the City of Dania Beach on

, 2011

CITY OF DANIA BEACH,

Public Services Department

By: 		By:

Name: Frederick Bloetscher, Ph.D., P.E			Dominic F. Orlando, P.E.

Project Management Consultant					Public Services Director

ATTACHMENT A

City of Dania Beach, Florida

DESIGN/BUILD SERVICES FOR THE CITY OF DANIA BEACH

2.0 MGD NANOFILTRATION WATER TREATMENT PLANT

CHANGE ORDER No. 7

Duplex Air Compressor

SCOPE OF CHANGE ORDER

This Change Order provides means of payment from the Owner’s Contingency.

This Change Order provides no net increase to the cost of the project.

This Change Order furnishes and installs a new a fully functioning duplex air compressor including electrical and auxiliary equipment. All materials and equipment shall be suitable for a high humidity environment exposed to the weather. The Change Order also provides a credit for two existing compressors and also includes the previous loaner cost for a standby compressor. This proposal excludes any modifications to the programming or the existing SCADA system.

ITEM

- Duplex Air Compressor …………………………………….….….……….….…   $13,690.00

Furnish and install one new two-stage, air-cooled, splash-lubed, reciprocating duplex air compressor, mounted on 200 gallon horizontal tank, with a 10 hp TEFC motor. Includes a new NEMA 4 pressure switch, and a new NEMA 4 single power source alternating control panel with starters.

- Compressor Equipment ………………………………………………………..….    $5,435.00

Furnish and install a non-cycling refrigerated air dryer, prefilter, oilescer filter, condensate separator, and 240 gallon cold tank.

- Electrical Equipment …………………………………………………………..….       $825.00

Furnishes and install a new heavy-duty NEMA 4 fused disconnect.

- Loaner Compressor ……………………………………………………………….      Included

Provide the City a standby tank mount compressor until the new units are installed.

- Trade-In Allowance ……………………………………………………………….    ($600.00)

Provide a credit for the City’s two existing compressors.

- Startup and Testing ………………………………………………………………..      $450.00

- Engineering Services ………………………………………………………………  $3,600.00

- Sales Tax ………………………………………………………………………….    $1,161.00

- Bonds and Insurance ……………………………………………......................…..      $781.00

- Design-Builders Overhead ……………………………………...…………………   $2,096.00

- Design Build Firm’s Fee ……..………….………………………………………...   $1,048.00

Total Change Order No. 7 Amount ……...…………..….….……...………...…. $28,486.00