Exhibit A

City of Dania Beach

Municipal Marina Project

Summary of Change Order Requests

CHANGE ORDER NO.1

- CHANGE ORDER REQUEST 1

Date Submitted:  3/19/13

Purpose:  Install sewer pump-out signage

Status:	Rejected, as it was deemed unnecessary since payment for the signs will come from the Project Signage Allowance pay Item.

Amount:  $0.00

- CHANGE ORDER REQUEST 2

Date Submitted:  3/22/13 (revised 6/7/13)

Purpose:  Construct expansion joints in seawall cap.

Justification:  Expansion joints in the seawall cap were not originally included in the bid set of plans since concrete mortar and pavers will be installed on top.  After further review with Shoreline, the Structural Engineers and the City, it was determined that expansion joints would be added to reduce cracking and possible movement of the pavers being installed on top of the wall.

Status:  Scope of work approved

Amount:  Will be negotiated not to exceed $3,344.23

- CHANGE ORDER REQUEST 3

Date Submitted:  4/2/13

Purpose:  Upgrading the wood mooring piles.

Status:	Rejected, as being unnecessary.

Amount:  $0.00

- CHANGE ORDER REQUEST 4

Date Submitted:  4/30/13 (revised 5/21/13)

Purpose:  Revision of the feeder wire from the FPL Transformer to the main electrical panel (Panel “DPA”).

Justification:  During Building Department permit review, the permitting agency questioned the sizing of feeder wires.  The Project Electrical Engineer determined that the feeder wire, while NOT technically undersized would not be capable of any power additions.  To ensure future upgradability of the Marina and to satisfy the Building Department’s concerns, the feeder wire was upsized.

Status:  Scope of work approved.

Amount:  Will be negotiated not to exceed $3,805.62

- CHANGE ORDER REQUEST 5

Date Submitted:  5/28/13 (revised 6/12/13)

Purpose:  Relocate A/C Condensers and install on raised stands, upsize circuits for dock lighting transformers and additional grounding & lightning protection on Kiosks & Pavilions.

Justification:  City Building Permit review comments on the electrical design caused increases in ground circuits, lightning protection and transformer sizes and City request to revise the fence & sidewalk layout caused a change in the design for location and mounting methods for the A/C condensers at the Dock Master Building.

Status:  Review Pending

Amount:  Will be negotiated not to exceed $43,067.74

- CHANGE ORDER REQUEST 6

Date Submitted:  8/13/13

Purpose:  Wall and door changes due to Fire Department review and comments.

Justification:  City Fire Department requirements during permit review.

Status:  Scope of work approved

Amount:  Will be negotiated not to exceed $5,877.12

- CHANGE ORDER REQUEST 7

Date Submitted:  6/5/13

Purpose:  Building Permit fee cost

Justification:  Amount of fees exceeded 2% of the total contract amount.

Status:  Change Order was negotiated between SFI and the City and the City’s Public Services Department paid $53,677.72.

Amount:  $0.00

- CHANGE ORDER REQUEST 8

Date Submitted:  6/13/13 (revised 8/5/13)

Purpose:  Fence, sidewalk, and landscape changes.

Justification:  City requested changes to fence alignment and sidewalk widths.

Status:  Scope of work approved

Amount:  Will be negotiated not to exceed $12,159.02

- CHANGE ORDER REQUEST 9

Date Submitted:  8/5/13

Purpose:  Kiosk and pavilion finish changes made via ASI #1 Directive.

Status:  Scope of work approved

Amount:  Will be negotiated not to exceed $18,820.76

- CHANGE ORDER REQUEST 10

Date Submitted:  7/11/13

Purpose: Changes to electrical panels due to adding circuits for the old Dock Master Building and the Sanitary Lift Station.

Justification:  Insufficient information existed during design to determine power source and loads to original Dock Master Building.  Construction excavation and demolition activities allowed the Electrical Engineers to make a final determination of power requirements.

Status:  Scope of work approved

Amount:  Will be negotiated not to exceed $34,717.50

- CHANGE ORDER REQUEST 11

Date Submitted:  7/1/13

Purpose:  Additional permit fees for the metal roof truss shop drawing review.

Status:  Rejected

Amount: $ 0.00

- CHANGE ORDER REQUEST 12

Date Submitted:  Pending

Purpose:  Additional jetting/blowing of excess materials for the gangways and Docks E and F

Justification:  Environmental permitting restraints required for protection of seagrass during dredging prevented the Contractor from excavating the entire footprint of the new docks.  Jetting the excess remaining materials will prevent the docks from hitting ground during extreme low tides. This tide event actually occurred during July and August

Status:  Review pending

Amount:  Will be negotiated not to exceed $10,000.00

- ALLOWANCE - $25,000.00 Not – to – Exceed

Project allowance to address unanticipated field conditions, required items to closeout Project, additional permits and permit modifications. All costs will be negotiated at actual cost total not to exceed $25,000.00

| City of Dania Beach |
| --- |
| Municipal Marina Project |
| Cost Summary |
| Change Order | Max. Amount |
| 1 | $ - |
| 2 | $ 3,344.23 |
| 3 | $ - |
| 4 | $ 3,802.62 |
| 5 | $ 43,067.74 |
| 6 | $ 5,887.12 |
| 7 | $ - |
| 8 | $ 12,159.02 |
| 9 | $ 18,820.76 |
| 10 | $ 34,717.50 |
| 11 | $ - |
| 12 | $ 10,000.00 |
| Allowance | $ 25,000.00 (NTE) |
| Total | $ 156,798.99 (NTE) |