TO:		Mayor Walter B. Duke, III

Vice Mayor Albert C. Jones

Commissioner Chickie Brandimarte

Commissioner Bobbie H. Grace

FROM:	Robert Baldwin, City Manager

VIA:		Dominic F. Orlando, P.E. Director of Public Services

Ronnie Navarro, P. E., City Engineer

Date:		September 24, 2013

RE:	Change Order No. 2 to Insituform Inc. for Infiltration and Inflow Phase 3 (no cost)

# Introduction and Background

FDEP approved State Revolving Funds for the Phase III Infiltration and Inflow program in August, 2011.  The City Commission submitted a loan application to FDEP for said funds in the Fall of 2011.  Advertisements for bids were placed in local papers on November 23, 2011 and bids were opened on Friday, January 13, 2012 at 10:30 am.  There were three bidders as follows:

Insituform			$774,398.50

Lanzo Construction		$832,832.00

Century Building		$962,005.25;

The Project Manager and City’s bid review team recommended that the City award the bid to the low bidder, Insituform, Inc. Resolution No. 2012-044 dated March 27, 2012 approved a ranking of bid responses and awarded a bid to Instituform, Inc. in the amount of $774,098.50 for Phase III of the Infiltration and Inflow program.

The quantities in the original bid were previously adjusted at no additional cost to the contract to reflect actual work done in the field. Change Order No. 1 was approved in Resolution No. 2013-013, dated January 22, 2013 at no cost to reflect actual quantities done to date at that time.

The quantities in the revised bid need to be adjusted again to reflect actual quantities completed in the field, but the changes do not result in an increase to the contract amount.  This would be Change Order No. 2 (attached) with quantities adjusted as shown on Attachment 1. Once Change Order No. 2 is approved, the work in this Contract is substantially completed. Staff recommends approval of no cost Change Order No. 2.

# Recommendation

It is recommended that the City Commission approve Change Order No. 2 at no increase in cost to the Contract with Insituform, Inc., and authorizes and directs the City Manager to execute same.

ATTCHMENT 1

| Item | Original Quantity | Unit | Unit Cost |  | Original Total cost |  | Revised Quantity |  | Revised Total cost |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mobilization | 1 | LS | $ 8,200.00 |  | $ 8,200.00 |  | 1 |  | $ 8,200.00 |
| Clean 8 inch piping identified on Appendix A map | 36,400 | LF | $ 0.90 |  | $ 32,760.00 |  | 32,186 |  | $ 28,967.40 |
| Clean 10 or 12 inch piping identified on Appendix A map | 650 | LF | $ 1.10 |  | $ 715.00 |  | 1800 |  | $ 1,980.00 |
| Clean 15 or 18 inch piping identified on Appendix A map | 1865 | LF | $ 1.70 |  | $ 3,170.50 |  | 24 |  | $ 40.80 |
| Televise 8 inch Piping identified on Appendix A map | 36,400 | LF | $ 0.40 |  | $ 14,560.00 |  | 32,186 |  | $ 12,874.40 |
| Televise 10 or 12 inch Piping identified on Appendix A map | 650 | LF | $ 0.40 |  | $ 260.00 |  | 1800 |  | $ 720.00 |
| Televise 15 or 18 inch Piping identified on Appendix A map | 1,865 | LF | $ 1.40 |  | $ 2,611.00 |  | 24 |  | $ 33.60 |
| Televise service line - up to 30 ft from connection | 2,500 | LF | $ 3.20 |  | $ 8,000.00 |  | 2,500 |  | $ 8,000.00 |
| 8 inch pipe lining | 10,000 | LF | $ 23.60 |  | $ 236,000.00 |  | 16,917 |  | $ 399,241.20 |
| 10 or 12 inch pipe lining | 500 | LF | $ 28.80 |  | $ 14,400.00 |  | 964 |  | $ 27,763.20 |
| 15 inch pipe lining | 500 | LF | $ 43.30 |  | $ 21,650.00 |  | 0 |  | $ - |
| 18 inch pipe lining | 500 | LF | $ 61.00 |  | $ 30,500.00 |  | 0 |  | $ - |
| Line non-metallic service laterals 4 or 6 in | 1,500 | LF | $ 35.40 |  | $ 53,100.00 |  | 546 |  | $ 19,328.40 |
| Line metallic service laterals 4 or 6 in | 1,500 | LF | $ 35.40 |  | $ 53,100.00 |  | 0 |  | $ - |
| Install full circle lateral connection to 8-12 in pipe with 4or 6 in lateral, plus 3 ft of liner pip | 50 | ea | $ 2,879.60 |  | $ 143,980.00 |  | 39 |  | $ 112,304.40 |
| Reconnect laterals | 100 | ea | $ 364.40 |  | $ 36,440.00 |  | 311 |  | $ 113,328.40 |
| Repairs to Manhole tops | 20 | VF | $ 252.60 |  | $ 5,052.00 |  | 0 |  | $ - |
| Point repairs – pipe and laterals (time and material+ 10 %) | 1 | LS | $50,000.00 |  | $ 50,000.00 |  | 1 |  | $ 19,426.00 |
| Traffic Control (time and material) | 1 | LS | $25,000.00 |  | $ 25,000.00 |  | 1 |  | $ - |
| Contingency | 1 | LS | $25,000.00 |  | $ 25,000.00 |  | 1 |  | $ 12,290.70 |
| Alternate 1 – Smoke Test | 1 | LS | $ 9,900.00 |  | $ 9,900.00 |  | 1 |  | $ 9,900.00 |
|  | TOTAL BID AMT |  |  |  | $ 774,398.50 |  |  |  | $ 774,398.50 |