## CHange ORder 1 - page 1
CHANGE ORDER | [6 empty] | PAGE ONE OF | 1 |  | PAGES 2
TO OWNER: | City of Dania Beach | CONTRACT FOR: | OASIS 4 |  | CHANGE ORDER NO: 01 |  |  | Distribution to:
1210 Hills
| 100 West Dania Beach Blvd. |  | SE 2nd St. | [5 empty] | OWNER
| Dania Beach, FL 33004 | [6 empty] | X | ENGINEER
X
[5 empty] | PERIOD TO: September 30, 2013 |  |  |  | CONTRACTOR
FROM CONTRACTOR: |  | VIA CONSULTANT:
| Straightline Engineering |  | Public Utility Management & Planning Services
| 15223 NW 33rd Pl |  | P. O. Box 221890
| Miami Gardens, FL 33054 |  | Hollywood, FL 33022-1890 |  | CONTRACT DATE: | July 15 2013
CONTRACTOR'S CHANGE ORDER |  |  |  | CONTRACTOR:
|  |  |  | By: |  |  |  | Date:
State of: Florida:_______________________
1. ORIGINAL CONTRACT SUM |  | $ | 74534 | County of: _______________________________
2. Prior Changes |  |  | 0 | Subscribed and sworn to before me this |  |  | day of
|  |  |  | Notary Public: | [5 empty] | .
3. Net change by this Change Order No |  | $ | 81411 | My Commission expires:
4. REVISED CONTRACT AMOUNT (Line 1 ± 2 +3) $ |  | $ | 155945
CITY OF DANIA BEACH, a Florida
Municipal corporation
By: _____________________________
Robert Baldwin, City Manager
|  |  |  | Authorized by action of City Commission of the City of Dania Beach on | [5 empty] | _____________, 2013.

## CO 1page 2
STRAIGHTLINE ENGINEERING
Address:
City of Dania Beach, OASIS 4 SE 2nd ST
Schedule of Values
Change Order No 1
A | B |  |  | C |  | D | E | F | G
| DESCRIPTION OF WORK |  |  |  |  | WORK
ITEM |  | INITITAL |  | UNIT | TOTAL
NO. |  | UNIT QTY | UNITS | PRICE | BID COST | REVISED QTY | NET QTY | FINAL PRICE | NET
BID
1 | Mobilization | 1 | LS | 15000 | 15000 | 1 | 0 | 15000 | 0
2 | Clearing and Demolition | 1 | LS | 7000 | 7000 | 1 | 0 | 7000 | 0
3 | Permit Allowance | 1 | LS | 5000 | 5000 | 1 | 0 | 5000 | 0
4 | "Oasis"-Type Street Signs | 9 | EA | 850 | 7650 | 4 | -5 | 3400 | -4250
5 | Permeable Pavers Bricks for swales | 870 | SF | 5 | 4350 | 2750 | 1880 | 13750 | 9400
6 | Street Brick Pavers for crosswalks | 1200 | cy | 4 | 4800 | 1200 | 0 | 4800 | 0
7 | Bedding Sand | 26 | cy | 18 | 468 | 35 | 9 | 630 | 162
8 | 4 in limerock base | 52 | cy | 13 | 676 | 65 | 13 | 845 | 169
9 | 12 in subbase | 100 | cy | 12 | 1200 | 200 | 100 | 2400 | 1200
10 | Entrance sign | 1 | EA | 750 | 750 | 2 | 1 | 1500 | 750
11 | Header Curb 8 x 12 inch | 650 | LF | 28 | 18200 | 1210 | 560 | 33880 | 15680
12 | FDOT Handicapped Ramps | 4 | EA | 500 | 2000 | 8 | 4 | 4000 | 2000
13 | Mail Boxes with Decorative Post | 10 | EA | 270 | 2700 | 10 | 0 | 2700 | 0
14 | Optional: 8-ft Trees (Silver Buttonwood) | 10 | EA | 250 | 2500 | 10 | 0 | 2500 | 0
15 | Optional: 12-inch bushes | 10 | EA | 9 | 90 | 10 | 0 | 90 | 0
16 | Sod, etc | 30 | SY | 5 | 150 | 750 | 720 | 3750 | 3600
17 | Handicapped Curbs | 4 | SY | 500 | 2000 | 8 | 4 | 4000 | 2000
18 | Remove and Replace Sidewalks | 0 | SF | 6 | 0 | 1000 | 1000 | 6000 | 6000
19 | Remove Asphalt | 0 | SF | 3 | 0 | 1000 | 1000 | 3000 | 3000
20 | Remove Grates, Install New Curb Inlets | 0 | EA | 2300 | 0 | 4 | 4 | 9200 | 9200
21 | Striping Removal | 0 | LS | 750 | 0 | 1 | 1 | 750 | 750
22 | Install Striping | 0 | LS | 1500 | 0 | 1 | 1 | 1500 | 1500
23 | Install Asphalt | 0 | SY | 50 | 0 | 500 | 500 | 25000 | 25000
24 | Reinforced Curbs | 0 | LF | 35 | 0 | 150 | 150 | 5250 | 5250
| GRAND TOTALS |  |  |  | 74534 |  |  | 155945 | 81411
Users may obtain validation of this document by requesting of the license a completed AIA Document D401 - Certification of Document's Authenticity