## G702
CHANGE ORDER | [5 empty] | PAGE ONE OF | 1 |  | PAGES 2
TO OWNER: | City of Dania Beach | PROJECT: | Lime Softening Plant |  | CHANGE ORDER NO: 1 |  | Distribution to:
1210 Hills
| 100 West Dania Beach Blvd. |  | Rehabilitation |  |  |  | X | OWNER
| Dania Beach, FL 33004 | [5 empty] | X | ENGINEER
X
CONTRACTOR
FROM CONTRACTOR: |  | VIA CONSULTANT:
| Close Construction, LLC. |  | Public Utility Management & Planning Services
| 301 NW 4th Avenue |  | P. O. Box 221890
| Okeechobee, FL 34972 |  | Hollywood, FL 33022-1890 |  | CONTRACT DATE: June 24, 2013
CONTRACTOR:
Application is made for payment, as shown below, in connection with the Contract.
Continuation Sheet, AIA Document G703, is attached.
|  |  |  | By: |  |  | Date:
State of: Florida:_______________________
1. ORIGINAL CONTRACT SUM |  | $ | 857830 | County of: _______________________________
2. Net change by Change Orders |  | $ | -16838.61 | Subscribed and sworn to before me this |  | day of
3. CONTRACT SUM TO DATE (Line 1 ± 2) $ |  | $ | 840991.39 | Notary Public: |  |  |  |  | .
My Commission expires:
CITY OF DANIA BEACH, a Florida
Municipal corporation
By: _____________________________
Robert Baldwin, City Manager
|  |  |  | Authorized by action of City Commission of the City of Dania Beach on |  |  |  |  | _____________, 2013.
AIA DOCUMENT G702 · APPLICATION AND CERTIFICATION FOR PAYMENT · 1992 EDITION · AIA · ©1992 |  |  |  | THE AMERICAN INSTITUTE OF ARCHITECTS, 1735 NEW YORK AVE., N.W., WASHINGTON, DC 20006-5292
Users may obtain validation of this document by requesting a completed AIA Document D401 - Certification of Document's Authenticity from the Licensee.
Note: Items in RED FONT are automatically calculated from the G703 form or from items within this G702 Form. Do NOT hand enter these items on this sheet.

## G703
Close Construction, LLC
301 NW 4th Avenue
Okeechobee, FL 34972
City of Dania Beach, Lime Softening Plant Rehabilitation - Accelator Repairs
Schedule of Values
A | B | C | D | E | F
| DESCRIPTION OF WORK |  | WORK COMPLETED
ITEM |  | SCHEDULED | FROM PREVIOUS |  | NET TO
NO. |  | VALUE | APPLICATION | TO COMPLETE | FINISH
(D + E)
1 | Owner Allowance - Permits & Metal Repair | 50000 | 190 |  | -49810
2 | Mobilization | 40000 | 40000 |  | 0
3 | Bonds / Insurance | 20000 | 20000 |  | 0
4 | Submittals | 10000 | 10000 |  | 0
5 | Stairs and Catwalks
6 | Remove Existing | 40000 | 40000 |  | 0
7 | Install New | 150000 | 120000 | 30000 | 0
8 | West Accelator
9 | Remove Existing Catwalk and Aerator | 25000 | 25000 |  | 0
10 | Repair Internals | 10000 | 10000 |  | 0
11 | Install new Catwalk | 105665 | 105665 |  | 0
12 | Install pipe and nozzles | 6500 | 4875 | 1625 | 0
13 | Install new Aerator | 30000 | 30000 |  | 0
14 | Install Drive Unit | 65000 | 48750 | 16250 | 0
15 | Start Up and Testing | 1500 |  | 1500 | 0
16 | Electrical Work
17 | Remove Existing Panel Boxes | 1500 | 750 | 750 | 0
18 | Install New Panel Boxes | 1500 | 750 | 750 | 0
19 | Disconnect & Reconnect West Drive | 1500 | 1500 |  | 0
20 | Disconnect & Reconnect East Drive | 1500 |  | 1500 | 0
21 | Disconnect & Reconnect Lime Feed Pumps | 1500 | 1500 |  | 0
22 | East Accelator
23 | Drain Acellator | 500 | 500 |  | 0
24 | Remove Existing Catwalk, Aerator & Drive Unit | 25000 | 25000 |  | 0
25 | Repair Internals | 10000 |  | 10000 | 0
26 | Install new Catwalk | 105665 | 84532 | 21133 | 0
26 | Install New Drive Unit | 65000 | 48750 | 16250 | 0
27 | Install pipe and nozzles | 6500 | 4875 | 1625 | 0
28 | Install Aerator | 30000 | 22500 | 7500 | 0
29 | Start Up and Testing | 1500 |  | 1500 | 0
30 | Lime System
31 | Remove Tank and install temp. Tank | 1500 | 1500 |  | 0
32 | Install New Tank | 3000 | 3000 |  | 0
33 | Remove & Install Lime Pump 1 | 16500 | 16500 |  | 0
34 | Remove & Install Lime Pump 2 | 16500 | 16500 |  | 0
35 | Start Up and Testing | 500 | 500 |  | 0
36 | Coatings | 10000 | 10000 |  | 0
37 | Demobilization | 4500 | 4500 |  | 0
38 | Change Order 2 Pans |  |  |  | 8808.03
39 | Change Order 3 - Pipe Supports and Coatings |  |  |  | 22988.96
40 | Change Order 5 - Accelator Screens |  |  |  | 1174.4
| GRAND TOTALS | 857830 | 697637 | 110383 | -16838.61
Users may obtain validation of this document by requesting of the license a completed AIA Document D401 - Certification of Document's Authenticity